## GanttChart
ProdUSE Project Schedule |  |  |  | (Instructions: Enter text & values in the Blue cells)
| Project Start Date: | 2024-09-20 |  | Display Week: | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
[6 empty] | 2024-09-16 | [6 empty] | 2024-09-23 | [6 empty] | 2024-09-30 | [6 empty] | 2024-10-07 | [6 empty] | 2024-10-14 | [6 empty] | 2024-10-21 | [6 empty] | 2024-10-28 | [6 empty] | 2024-11-04 | [6 empty] | 2024-11-11 | [6 empty] | 2024-11-18 | [6 empty] | 2024-11-25 | [6 empty] | 2024-12-02 | [6 empty] | 2024-12-09
 | time axis 2024-09-16 to 2024-12-15
| TASK | LEADER | START | DAYS | END | time axis 2024-09-16 to 2024-12-15
1 | Requirements Document |  |  |  | -
.1 | Create project timeline | Emme | 2024-09-19 | 5 | 2024-09-23
.1 | Define deliverables | Emme | 2024-09-19 | 5 | 2024-09-23
.1 | Define project scope | Emme / All | 2024-09-19 | 5 | 2024-09-23
.1 | Create list/hierarchy of goals for project | All | 2024-09-23 | 1 | 2024-09-23
.1 | Draft document | All | 2024-09-23 | 1 | 2024-09-23
.1 | Revise document | All | 2024-09-23 | 7 | 2024-09-29
.1 |  |  |  |  | -
1 | Design Documents |  |  |  | -
.1 | Create user personas (2-3) | [Task Leader Name] | 2024-09-26 | 5 | 2024-09-30
.1 | Create storyboards for app interactions | [Task Leader Name] | 2024-09-30 | 5 | 2024-10-04
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
1 | Database |  |  |  | -
.1 | Have basic understanding/background of SQLite and database schemas | [Task Leader Name] | 2024-09-23 | 7 | 2024-09-29
.1 | Create draft of database schema (graphical or text) based on initial project goals/requirements | [Task Leader Name] | 2024-09-30 | 7 | 2024-10-06
.1 | Update schema based on user feedback, create list of functions | [Task Leader Name] | 2024-10-14 | 2 | 2024-10-15
.1 | Create database schema using SQLite | [Task Leader Name] | 2024-10-14 | 7 | 2024-10-20
.1 | Create test data for app | [Task Leader Name] | 2024-10-19 | 4 | 2024-10-22
.1 | Implement database functions | [Task Leader Name] | 2024-10-23 | 12 | 2024-11-03
.1 | Test functions | [Task Leader Name] | 2024-10-30 | 5 | 2024-11-03
1 | UI Design |  |  |  | -
.1 | Create lo-fi paper prototypes | [Task Leader Name] | 2024-09-30 | 7 | 2024-10-06
.1 | Integrate user feedback from 1st round of usability testing | [Task Leader Name] | 2024-10-14 | 5 | 2024-10-18
.1 | Create wireframes in Figma | [Task Leader Name] | 2024-10-19 | 5 | 2024-10-23
.1 | Update wireframes with 2nd round of feedback | [Task Leader Name] | 2024-10-28 | 7 | 2024-11-03
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
1 | App Home Page |  |  |  | -
.1 | Create front end UI | [Task Leader Name] | 2024-10-14 | 7 | 2024-10-20
.1 | Add back-end functionality | [Task Leader Name] | 2024-10-21 | 7 | 2024-10-27
.1 | Integrate database | [Task Leader Name] | 2024-10-28 | 7 | 2024-11-03
.1 | Make changes based on user testing | [Task Leader Name] | 2024-11-09 | 4 | 2024-11-12
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
1 | Produce Details Page |  |  |  | -
.1 | Create app navigation | [Task Leader Name] | 2024-11-04 | 3 | 2024-11-06
.1 | Create front end UI | [Task Leader Name] | 2024-11-06 | 5 | 2024-11-10
.1 | Add back end functionality | [Task Leader Name] | 2024-11-11 | 7 | 2024-11-17
.1 | Integrate database | [Task Leader Name] | 2024-11-11 | 7 | 2024-11-17
.1 | Make changes based on user testing | [Task Leader Name] | 2024-11-16 | 4 | 2024-11-19
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
1 | Add/Edit Produce Page |  |  |  | -
.1 | Add app navigation | [Task Leader Name] | 2024-11-04 | 3 | 2024-11-06
.1 | Create front end UI | [Task Leader Name] | 2024-11-06 | 5 | 2024-11-10
.1 | Add back end functionality | [Task Leader Name] | 2024-11-11 | 7 | 2024-11-17
.1 | Integrate database | [Task Leader Name] | 2024-11-11 | 7 | 2024-11-17
.1 | Make changes based on user testing | [Task Leader Name] | 2024-11-16 | 4 | 2024-11-19
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
1 | Metrics and Tracking Page |  |  |  | -
.1 | Add app navigation | [Task Leader Name] | 2024-11-04 | 3 | 2024-11-06
.1 | Create front end UI | [Task Leader Name] | 2024-11-06 | 7 | 2024-11-12
.1 | Add back end functionality | [Task Leader Name] | 2024-11-18 | 7 | 2024-11-24
.1 | Integrate database | [Task Leader Name] | 2024-11-18 | 7 | 2024-11-24
.1 | Make changes based on user testing | [Task Leader Name] | 2024-12-04 | 5 | 2024-12-08
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
.1 |  |  | 2024-09-16 | 0 | 2024-09-16
1 | User Testing |  |  |  | -
.1 | Create materials and tasks for initial user feedback (inform app features and database schema) | [Task Leader Name] | 2024-09-30 | 7 | 2024-10-06
.1 | Get feedback on lo-fi app prototypes and initial materials (general layout and features) | [Task Leader Name] | 2024-10-07 | 7 | 2024-10-13
.1 | Get feedback on Figma wireframes for app | [Task Leader Name] | 2024-10-24 | 4 | 2024-10-27
.1 | Test app home page | [Task Leader Name] | 2024-11-04 | 5 | 2024-11-08
.1 | Test produce details page | [Task Leader Name] | 2024-11-18 | 5 | 2024-11-22
.1 | Test add/edit produce page | [Task Leader Name] | 2024-11-18 | 5 | 2024-11-22
.1 | Test metrics page | [Task Leader Name] | 2024-12-02 | 5 | 2024-12-06
1 | Deliverables |  |  |  | -
.1 | Deliverable 1: Requirements Document | [Task Leader Name] | 2024-09-23 | 7 | 2024-09-29
.1 | Deliverable 2: Design document(s) | [Task Leader Name] | 2024-09-30 | 7 | 2024-10-06
.1 | Deliverable 3: Database schema and user feedback | [Task Leader Name] | 2024-10-07 | 14 | 2024-10-20
.1 | Deliverable 4: App home page with database integration | [Task Leader Name] | 2024-10-21 | 14 | 2024-11-03
.1 | Deliverable 5: Produce details page and add/edit produce page | [Task Leader Name] | 2024-11-04 | 14 | 2024-11-17
.1 | Final deliverable: Preview build of completed app | [Task Leader Name] | 2024-11-18 | 21 | 2024-12-08
.1 | Final deliverable: App documentation | [Task Leader Name] | 2024-11-18 | 21 | 2024-12-08
.1 | Final presentation | [Task Leader Name] | 2024-11-18 | 21 | 2024-12-08
Gantt Chart Template © 2006-2018 by Vertex42.com.